## 4thQt_Week 1-2
Computer Science 2 Project | Team Members: | Zian Padillo
Group Progress Report |  | Marcus Elona
4th Quarter
Week 1-2 - March 2-13, 2026
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
\Began working on pseudocode for visualization
Begin formatting the initial design of the pagr |  | Finished pseudocode and we are ready to begin coding backend and frontend software
STRENGTH
Clear sense of direction
The simplicity of pseudocodes
AREAS FOR DEVELOPMENT
Actual Calculations
Information Storage
STRATEGY FOR SUCCESS
Maintain consistency in working on the software

## 4thQt_Week 3-4
Computer Science 2 Project | Team Members: | Zian Padillo
Group Progress Report |  | Marcus Elona
4th Quarter
Week 3-4 - March 16-27, 2026
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Began working on the backend python code |  | Initial backends completed
Complete initial backend program |  | Most functions implemented
Logic flow mostly works
Add all functios into the backend
STRENGTH
We have experience in all the functions we need because of the studying from last quarter
Simplifiction of operations
AREAS FOR DEVELOPMENT
Depth of assessment value
STRATEGY FOR SUCCESS
Remain consistent and begin working on the frontend

## 4thQt_Week 5-6
Computer Science 2 Project | Team Members: | Zian Padillo
Group Progress Report |  | Marcus Elona
4th Quarter
Week 5-6 - March 30-April 5
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Create basic frontend code using HTML
Begin fusing the backend to the frontend |  | Initial frontend code completed
Debug the backend for any errors |  | Fusion partially completed
STRENGTH
Our HTML knowledge is deep enough to make the frontend
The backend is already ready to fuse
AREAS FOR DEVELOPMENT
Bugs and other logical errors
Frontend design
STRATEGY FOR SUCCESS
Continue research on HTML

## 4thQt_Week 7
Computer Science 2 Project | Team Members: | Zian Padillo
Group Progress Report |  | Marcus Elona
3rd Quarter
Week 7 - April 6-7
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Implement assessment types |  | Code refined
Refine frontend |  | Assessment types flawlessly implemented
Polish to extinguish bugs |  | Edited UI
STRENGTH
Code is almost complete
A few simple fixes are necessary
AREAS FOR DEVELOPMENT
GUI
Logic Flow
Assessment Type
STRATEGY FOR SUCCESS
Properly track time usage to allow
focusing on other tasks needed to be
finished