## week1
Computer Science 2 Project | Team Members: | Zian Andre Padillo
Group Progress Report |  | Marcus Paul Elona
3rd Quarter
Week 1 - Jan 16, 2026
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Revisit and double-check the project proposal | Finalized set of deadlines for each feature of the project | We have revisited and double-checked the project proposal and ensured that the following goals can be met by their respective deadline
Plan out the smaller functions of the program | Refreshed knowledge of basic code structures and various tools that will be useful | Our knowledge of Python topics have been refreshed and we will revisit these topics weekly
Create an initial structure of the code | Beginning of learning more advanced Python concepts
STRENGTH
We have indentified more clearly the programming skills we need to develop for the code.
We (I) already prior experience in web development.
We have downloaded the necessary tools to use for the development of our program.
AREAS FOR DEVELOPMENT
Project Proposal
Coding Skills
Structure Development
STRATEGY FOR SUCCESS
We won't rush the progress of our code. The first days of the week (Sat-Mon) will be used to refine our skills. The next half (Tue-Thu) will be used for creating the actual code. This is to avoid burn out and help us retain the momentum we have.

## week2
Computer Science 2 Project | Team Members:
Group Progress Report
3rd Quarter
Week 2 - Jan 23, 2026
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Begin coding core functions of finalized features | The usage of new functions such as try-except (to redirect an incorrect input type to an error message instead of crashing the program)
Continue learning more and more useful functions through various video and online resources | Found new Python channels with multiple tutorials on more advanced libraries and functions
STRENGTH
New, refreshed motivation
Solid plan formed
Code basics already formed
AREAS FOR DEVELOPMENT
Actual Code
Syntax Knowledge
Project Proposal (if deemed necessary)
STRATEGY FOR SUCCESS
Continue working on the core functions of the code and perfect them over the next few weeks to have the first prototype ready by mid February of early March

## week3
Computer Science 2 Project | Team Members:
Group Progress Report
3rd Quarter
Week 3 - Jan 30, 2026
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Begin the coding of the grade calculation sub-function | Initial core structure related to grade filtering and calculation | Core sub-function completed
Plan the input-output sequence |  | Coding on input-output begins
STRENGTH
Very deep knowledge on common functions (due to previous studies in previous weeks)
Good planning skills
AREAS FOR DEVELOPMENT
Input-output code
Creativity factor in grade calculation and display
STRATEGY FOR SUCCESS
Code in bits to not get overwhelmed so easily

## week4
Computer Science 2 Project | Team Members:
Group Progress Report
3rd Quarter
Week 4 - Feb 6, 2026
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Finish a rough outline of the input-output sequence | Input-output revision and validation | Rough input-output sequence completed
Polish the existing calculation code to ensure the smooth incorporation of the 2 codes | Variable manipulation techniques | Polishing unfinished but will be continued throughout the next week
STRENGTH
Developed understanding of the necessary functions
Clear goal setting and implementation
AREAS FOR DEVELOPMENT
Input-output sequence (polishing)
Calculation (polishing)
STRATEGY FOR SUCCESS
Follow the same strategy as last week to not get distracted nor overwhelmed